## Sheet1
User Story | Assignee | Nisum Resource Name | Present Status | Story Summary | Created | Updated
NEX-4530 | vinodp@BACKROADS.com | Khaleel | In Development | Presearch Grid Report | 2019-10-04 08:10 | 2019-12-09 16:22
NEX-4716 | vinodp@BACKROADS.com | Khaleel | In Development | Leader Changes after final count | 7/25/2019 15:38 | 2019-11-09 15:51
NEX-4627 | vinodp@BACKROADS.com | Shiva | In Development | Last Minute Changes to FTU - Through History Tables | 5/21/2019 15:38 | 2019-11-09 12:25
NEX-4291 | amandal@backroads.com | Sai Sadanala | In Development | Passport Changes for "SPECIAL" Trips Departing within 75 Days Report | 2018-04-12 13:24 | 8/29/2019 10:05
NEX-4593 | steven_biddinger@BACKROADS.com | Balaji | UAT | Departure Cancellations This Week - SubCons | 2019-09-05 13:31 | 2019-12-09 18:27
NEX-4731 | vinodp@BACKROADS.com | Balaji | UAT | Ship Trips Hitting Penalties | 2019-06-08 08:13 | 2019-12-09 16:25
NEX-3879 | vinodp@BACKROADS.com | Shiva | UAT | Guest Focus Cases â€“ Detail by Type & Subtype (YTD, 3 Yrs) | 7/31/2018 10:55 | 2019-12-09 15:48
NEX-4780 | emily_carson@backroads.com | Khaleel | UAT | Update to Sales - Memos by Creator report | 2019-04-09 08:30 | 2019-12-09 14:02
NEX-3890 | michael_bernhard@backroads.com | Sai Sadanala | UAT | Guest Evaluations on Backroads - AmaWaterways River Cruise Trips - as of <mm/dd/yyyy> | 7/31/2018 11:54 | 2019-12-09 14:00
NEX-4676 | jesse_karp@backroads.com | Shiva | UAT | BUG: Hotel Status Report Issues | 2019-02-07 16:12 | 2019-12-09 12:19
NEX-4783 | steven_biddinger@BACKROADS.com | Khaleel | UAT | TVR Subscription Updates | 2019-05-09 11:38 | 2019-11-09 15:17
NEX-3836 | vinodp@BACKROADS.com | Satya | UAT | Leader Development - Did you have fun? YTD - FTR | 7/30/2018 10:27 | 2019-11-09 12:25
NEX-4726 | steven_biddinger@BACKROADS.com | Shiva | UAT | Permits Contract Through | 2019-02-08 17:17 | 2019-11-09 12:19
NEX-3993 | vinodp@BACKROADS.com | Satya | UAT | Backroads IATA - Agency Report for Guests travelling <year> - NEED BY AUG 26th | 2018-01-08 13:12 | 2019-11-09 12:09
NEX-4753 | cat_malone@backroads.com | Balaji | UAT | BUG: Trip Ownership List | 8/15/2019 10:37 | 2019-11-09 11:15
NEX-4754 | kyle_zick@backroads.com | Satya | UAT | 6 or More E-bike Report | 8/15/2019 13:54 | 2019-10-09 12:22
NEX-3881 | stacyl@BACKROADS.com | Shiva | UAT | Guest Focus Cases â€“ Weekly Summary by Owner | 7/31/2018 11:02 | 2019-10-09 10:59
NEX-4682 | steven_biddinger@BACKROADS.com | Balaji | UAT | Orphaned Dates | 2019-08-07 14:24 | 2019-09-09 11:20
NEX-3700 | louieo@backroads.com | Satya | UAT | Private Trip Booking Trend - Weekly Report | 7/25/2018 12:30 | 2019-09-08 09:32
NEX-3631 | amandal@backroads.com | Satya | UAT | Bookings/Holds-Waitlists/Cancellations for "SPECIAL" Trips Report | 7/23/2018 18:12 | 2019-11-06 11:25
NEX-3731 | amandal@backroads.com | Satya | Done | PIF - Dietary Restrictions Report | 7/25/2018 19:53 | 2019-11-09 14:19
NEX-4631 | jesse_karp@backroads.com | Balaji | Done | On Demand Product Event Volume Report | 5/22/2019 13:41 | 2019-10-09 10:24
NEX-4784 | steven_biddinger@BACKROADS.com | Sai Sadanala | Done | BUG: Legacy Codes not appearing in TVR Report | 2019-05-09 13:21 | 2019-09-09 09:29
NEX-4705 | emily_carson@backroads.com | Satya | Done | Update to Memos by Creator Report | 7/19/2019 10:45 | 2019-06-09 10:36
NEX-4778 | richardw@backroads.com | Sai Sadanala | Done | TPC Archive Report (cont) | 2019-03-09 15:11 | 2019-05-09 10:43
NEX-4775 | steven_biddinger@BACKROADS.com | Khaleel | Done | TVR Report Auto-Send Issue | 2019-03-09 11:15 | 2019-04-09 12:40
NEX-4730 | hilary_breuner@backroads.com | Balaji | Done | Low Score Alert - Support Leader | 2019-05-08 13:02 | 2019-04-09 12:18
NEX-4484 | hilary_breuner@backroads.com | Satya | Done | On Demand - FTRs Submitted for a Selected Trip Departure | 3/21/2019 14:32 | 2019-04-09 11:11
NEX-4707 | richs@backroads.com | Shiva | Done | Modification to Reservations by Creation Date Report | 7/19/2019 16:02 | 2019-04-09 10:09
NEX-4401 | richardw@backroads.com | Balaji | Done | Web Trip Page - Archive a Trip due to Pended or Pvt Status | 1/31/2019 9:35 | 2019-03-09 15:11
NEX-4685 | arianas@BACKROADS.com | Sai Sadanala | Done | Ships Sales Report Request | 2019-10-07 14:49 | 2019-03-09 08:31
NEX-4523 | vinodp@BACKROADS.com | Shiva | Done | Re-write Web Trip Page Archive Report | 2019-02-04 16:54 | 8/30/2019 12:04
NEX-4741 | ruths@BACKROADS.com | Khaleel | Done | Modification: Transport Vendor Update - Roles | 2019-12-08 14:27 | 8/28/2019 11:36
NEX-4750 | ruths@BACKROADS.com | Satya | Done | Update Subscription for Low Score OE and Low Score Leader Alerts - Confidential Concerns? | 8/14/2019 7:52 | 8/28/2019 11:23
NEX-4648 | carlino@BACKROADS.com | Balaji | Done | Closed Departures | 2019-06-06 14:39 | 8/28/2019 9:28
NEX-4759 | ruths@BACKROADS.com | Sai Sadanala | Done | Update to Outstanding release form subscription | 8/22/2019 8:17 | 8/27/2019 11:45
NEX-4744 | katie_whitcomb@backroads.com | Sai Sadanala | Done | Data Dump of low scores (7 or below) submitted from May 1st 2019 | 8/13/2019 8:39 | 8/27/2019 0:13
NEX-4383 | carlosg@BACKROADS.com | Balaji | Done | New Private Trips Added Today Email | 1/25/2019 9:19 | 8/26/2019 15:31
NEX-3774 | kch@backroads.com | Shiva | Done | Backroads <year>-<year> Booking Report for TA Fam Discounts (by Transaction Date) | 7/27/2018 11:09 | 8/26/2019 13:06
NEX-4738 | ruths@BACKROADS.com | Khaleel | Done | Update to Cabins Released to Supplier | 2019-08-08 15:55 | 8/22/2019 16:22
NEX-4740 | jesseb@backroads.com | Balaji | Done | Product Audit | 2019-12-08 09:51 | 8/22/2019 14:47
NEX-3863 | cat_malone@backroads.com | Sai Sadanala | Done | ID8.3.26 - Trip Ownership List (formerly RM task lists) | 7/30/2018 16:41 | 8/21/2019 12:50
NEX-4752 | kyle_zick@backroads.com | Satya | Done | Add Height/Bike info to Equipment List Report | 8/15/2019 10:13 | 8/21/2019 9:44
NEX-4710 | ruths@BACKROADS.com | Venkatadri | Done | Update subscription filter on the Outstanding Guest Release Form | 2019-11-07 11:18 | 8/21/2019 8:02
NEX-4350 | hilary_breuner@backroads.com | Shiva | Done | Guest Eval Overall Experience Score (YTD) | 2019-04-01 13:42 | 8/21/2019 6:59
NEX-4739 | richs@backroads.com | Sai Sadanala | Done | BUG: Marketing Discount Savings Forecasting by Trip Departure Date | 2019-12-08 08:57 | 8/20/2019 16:26
NEX-4633 | jenniferp@BACKROADS.com | Satya | Done | Daily PDP Fulfillment ** | 5/22/2019 15:35 | 8/19/2019 10:09
NEX-4688 | arunb@backroads.com | Khaleel | Done | Duplicate/Triplicate Entry Issues on the TVR report | 2019-12-07 09:56 | 8/15/2019 11:12
NEX-4721 | riley_pearce@backroads.com | Khaleel | Done | Put Cost Worksheet Report into Softrip ** | 7/30/2019 15:36 | 2019-12-08 19:32
NEX-3897 | daniel_wootton@BACKROADS.com | Shiva | Done | Trip Scores Report (Detail) | 7/31/2018 12:12 | 2019-12-08 13:17
NEX-3828 | daniel_wootton@BACKROADS.com | Balaji | Done | ID8.3.17 - Trip Division List - Need for June | 7/30/2018 10:03 | 2019-12-08 13:16
NEX-4677 | riley_pearce@backroads.com | Satya | Done | FTR Feedback - Last 7 days | 2019-03-07 10:27 | 2019-12-08 13:16
NEX-4706 | kch@backroads.com | Balaji | Done | TA Report Validation | 7/16/2019 11:57 | 2019-12-08 10:32
NEX-4700 | kch@backroads.com | Satya | Done | Enhancement to Agency Reservations by Creation Date Report | 7/17/2019 15:05 | 2019-12-08 09:30
NEX-4722 | arunb@backroads.com | Khaleel | Done | TVR Updates | 7/30/2019 16:44 | 2019-12-08 09:21
NEX-4689 | arianas@BACKROADS.com | Balaji | Done | Cabins Released to Supplier for Resale Report ** | 2019-10-07 16:23 | 2019-08-08 15:55
NEX-4704 | emily_carson@backroads.com | Satya | Done | Updates to Memos by action Code Report | 7/19/2019 10:21 | 2019-08-08 12:01
NEX-4718 | ruths@BACKROADS.com | Satya | Done | Supplier Deposit Report ** | 7/19/2019 16:30 | 2019-06-08 14:35
NEX-4695 | kch@backroads.com | Khall | Done | BUG: Travel Agency Booking Report | 7/16/2019 8:54 | 2019-05-08 15:26
NEX-4656 | steven_biddinger@BACKROADS.com | Khaleel | Done | Services Entered as Departure Deviations (Product Detail Exceptions) Are Not Pulling into TVR Report | 6/17/2019 19:04 | 2019-05-08 10:00
NEX-4708 | liz_barry@backroads.com | Satya | Done | Update to Upcoming Messages Report | 7/19/2019 16:22 | 2019-02-08 12:51
NEX-4684 | kyle_zick@backroads.com | Balaji | Done | Add Leader Height and Bike Size Data from Legacy to the Equipment List report | 2019-08-07 10:35 | 2019-02-08 08:35
NEX-4671 | ruths@BACKROADS.com | Shiva | Done | Departure List by Date Range | 6/27/2019 16:08 | 2019-02-08 08:19
NEX-4717 | riley_pearce@backroads.com | Satya | Done | Data Dump - Supplier Feedback | 7/25/2019 14:34 | 2019-01-08 17:34
NEX-3883 | daniel_wootton@BACKROADS.com | Shiva | Done | Comparative Overall Experience Scores Report - Need for June** | 7/31/2018 11:11 | 7/30/2019 16:34
NEX-4701 | jenniferp@BACKROADS.com | Satya | Done | PGI Attribute Report from Softrip ** | 7/18/2019 11:07 | 7/30/2019 9:50
NEX-4702 | jenniferp@BACKROADS.com | KhAleel | Done | TP-LINK Attribute Report from Softrip ** | 7/18/2019 11:10 | 7/30/2019 9:49
NEX-4713 | steven_biddinger@BACKROADS.com | KhAleel | Done | Automate sending of Suppliers Requiring Insurance Report | 7/24/2019 12:41 | 7/29/2019 9:51
NEX-3668 | sean_faley@backroads.com | Balaji | Done | Guest Quality Issues | 7/24/2018 17:14 | 7/26/2019 11:25
NEX-4703 | vinodp@BACKROADS.com | Sai Sadanala | Done | Update to: Guest Evaluation Comment Detail - Equipment (Weekly) | 7/19/2019 8:37 | 7/26/2019 9:24
NEX-3627 | richs@backroads.com | Khaleel | Done | Guests with Trip Insurance by Departure Date - <year> vs. <year> | 7/23/2018 17:07 | 7/25/2019 8:25
NEX-4654 | tommaso_spinelli@BACKROADS.com | Sai Sadanala | Done | Enhancements to FieldStaff Overview Power BI - Part 2 (percentiles and delta, New Columns) | 6/18/2019 12:11 | 7/24/2019 11:27
NEX-4591 | lynny_kramm@BACKROADS.com | Shiva | Done | Guest Information for Family Trips | 2019-08-05 14:47 | 7/24/2019 9:32
NEX-4678 | jenniferp@BACKROADS.com | Balaji | Done | Update to the 50 Day Apparel Label List | 2019-03-07 13:32 | 7/24/2019 8:52
NEX-4460 | hilary_breuner@backroads.com | Satya | Done | On Demand â€“ FTRs Submitted for a Selected Guest | 2019-07-03 08:16 | 7/23/2019 18:46
NEX-4667 | tommaso_spinelli@BACKROADS.com | Sai Sadanala | Done | Enhancements to FieldStaff Overview Power BI - Part 3 (Seniority, LPF) | 6/27/2019 10:40 | 7/22/2019 10:24
NEX-4658 | bobg@backroads.com | Balaji | Done | Logistics Equipment Needs Weekly Report Update | 6/24/2019 14:54 | 7/22/2019 10:18
NEX-4475 | stevenz@BACKROADS.com | Balaji | Done | Upcoming Messages Report | 3/14/2019 16:16 | 7/19/2019 16:28
NEX-4659 | kevins@backroads.com | Khaleel | Done | Softrip Report needed for Finance | 6/25/2019 11:12 | 7/19/2019 7:41
NEX-4680 | jenniferp@BACKROADS.com | Sai Sadanala | Done | Update: TShirt Jersey Inventory(Weekly) Report | 2019-08-07 12:09 | 7/16/2019 7:58
NEX-4537 | hilary_breuner@backroads.com | Balaji | Done | Trip Quality, Weekly - Guest and Leader Comments | 4/16/2019 17:39 | 2019-08-07 17:44
NEX-4496 | jesse_karp@backroads.com | Shiva | Done | Dates Request Status Report (aka Hotel Status Report) | 3/25/2019 17:12 | 2019-03-07 11:13
NEX-3735 | daveb@backroads.com | Shiva | Done | Backroads Account Release Forms report ** | 7/25/2018 20:06 | 2019-02-07 12:31
NEX-4650 | arianas@BACKROADS.com | Satya | Done | Enhancements to the Vacancy Report | 2019-10-06 15:05 | 2019-02-07 12:01
NEX-4668 | jenniferp@BACKROADS.com | KhAleel | Done | Create Subscription for Fulfillment Request Memos | 6/27/2019 12:43 | 6/28/2019 13:13
NEX-4669 | jenniferp@BACKROADS.com | Satya | Done | Create Subscription for Resend Guest Docs Memos | 6/27/2019 12:45 | 6/28/2019 13:12
NEX-4617 | bobg@backroads.com | Balaji | Done | Bike Item Requests | 5/17/2019 9:45 | 6/28/2019 13:05
NEX-4652 | amandal@backroads.com | Khaleel | Done | Updates for PIF - Dietary Restrictions Report | 2019-12-06 07:58 | 6/28/2019 11:57
NEX-4647 | ruths@BACKROADS.com | Sai Sadanala | Done | Update: Departure Cancellations This Week - Hotels | 2019-06-06 12:14 | 6/27/2019 11:32
NEX-4649 | tommaso_spinelli@BACKROADS.com | Sai Sadanala | Done | Enhancements to FieldStaff Overview Power BI - Part 1 (#of evals) | 2019-10-06 09:54 | 6/27/2019 1:33
NEX-4437 | vinodp@BACKROADS.com | KhAleel | Done | ID8.2.3 - Subcontractor Dates Request Status** | 2/22/2019 8:12 | 6/25/2019 14:51
NEX-4638 | matt_fletcher@BACKROADS.com | Balaji | Done | Updates to the Logistics Equipment Report (6 versions) | 5/29/2019 9:14 | 6/24/2019 11:08
NEX-4628 | kyle_zick@backroads.com | Sai Sadanala | Done | Weekly Subscription: Guests Signed Up for Adult Bikes (incl Carbon Upgrades / Tandems / E-Bikes)** | 5/22/2019 8:00 | 6/24/2019 11:07
NEX-4622 | kyle_zick@backroads.com | Satya | Done | Updates to Cancellations of Carbon Bikes | 5/20/2019 14:20 | 6/24/2019 11:06
NEX-4607 | daveb@backroads.com | Khaleel | Done | TC Evaluation Performance Report Update | 5/14/2019 12:52 | 6/24/2019 11:00
NEX-4545 | kyle_zick@backroads.com | Balaji | Done | Unit Bike Needs | 4/23/2019 8:01 | 6/23/2019 21:52
NEX-4399 | amandal@backroads.com | Satya | Done | New Reservations Attachment for 48 Hour Email Queue -Meet Location Description and Time, Leader Info | 1/30/2019 15:45 | 6/17/2019 12:40
NEX-3803 | richs@backroads.com | Shiva | Done | ID10.10 - Booking Log | 7/27/2018 14:47 | 6/14/2019 14:34
NEX-4481 | steven_biddinger@BACKROADS.com | Balaji | Done | Transport Vendor Update | 3/21/2019 9:42 | 2019-11-06 11:56
NEX-4585 | stevenz@BACKROADS.com | Satya | Done | Vacancy Report - Ships ** | 2019-06-05 15:54 | 2019-11-06 11:17
NEX-4644 | vinodp@BACKROADS.com | Sai Sadanala | Done | Update: Low Score Alert email notification | 2019-03-06 15:53 | 2019-10-06 15:46
NEX-3609 | sean_faley@backroads.com | Khaleel | Done | Bike Fit Info Report (for Leaders) ** | 7/22/2018 15:49 | 2019-10-06 13:39
NEX-4642 | kch@backroads.com | Sai Sadanala | Done | Enhancement: Update Travel Agency Booking Report | 5/31/2019 15:48 | 2019-10-06 10:34
NEX-3637 | daveb@backroads.com | Balaji | Done | Outstanding Release Forms (trips departing <Month> <year>) Report | 7/23/2018 18:41 | 2019-07-06 10:43
NEX-4643 | jenniferp@BACKROADS.com | Satya | Done | 50 day apparel Label List ** | 2019-03-06 12:17 | 2019-07-06 09:16
NEX-4589 | jenniferp@BACKROADS.com | Satya | Done | 50 day apparel report** | 2019-08-05 08:51 | 2019-07-06 09:16
NEX-4477 | stevenz@BACKROADS.com | KhAleel | Done | Departure Cancellations This Week - Hotels | 3/19/2019 10:52 | 2019-06-06 12:14
NEX-4598 | cat_malone@backroads.com | Khaleel | Done | Update Trip Ownership report for CMS changes to Roles | 2019-10-05 08:59 | 2019-06-06 08:57
NEX-4590 | vinodp@BACKROADS.com | Venkatadri | Done | Update Power BI for CMS Role Changes | 2019-08-05 09:22 | 2019-04-06 12:54
NEX-4605 | jennac@BACKROADS.com | Satya | Done | LDR ACC Supplier Request ** | 5/13/2019 16:38 | 2019-03-06 16:07
NEX-4552 | bobg@backroads.com | Venkatadri | Done | Guest Evaluation Comment Detail - Equipment (Weekly) | 4/24/2019 7:44 | 2019-03-06 08:56
NEX-4577 | bobg@backroads.com | Satya | Done | TShirt Jersey Inventory (Monthly) | 2019-02-05 14:53 | 2019-03-06 08:55
NEX-4586 | bobg@backroads.com | Venkatadri | Done | Guests Signed Up for Adult Bikes (incl Carbon Upgrades / Tandems / E-Bikes)** | 2019-07-05 08:09 | 2019-03-06 08:54
NEX-3639 | jillt@backroads.com | Balaji | Done | ID2.4.2 - BEST Credits Applied / Issued - Daily | 7/24/2018 11:33 | 5/29/2019 14:34
NEX-3799 | louieo@backroads.com | Sai Sadanala | Done | Private Make/Take/Custom Trips Departing: <Month> <Year> Report | 7/27/2018 14:20 | 5/28/2019 14:08
NEX-3750 | leem@backroads.com | Khaleel | Done | ID17.6 - Custom Report For Catalog | 7/26/2018 12:02 | 5/23/2019 11:53
NEX-4152 | richs@backroads.com | Venkatadri | Done | TC Activity Log (originally Daily Cancel Fee Log) - COMPLEX | 11/13/2018 16:26 | 5/23/2019 11:53
NEX-4541 | louieo@backroads.com | Sai Sadanala | Done | Guest List Invoicing Detail | 4/22/2019 14:07 | 5/23/2019 11:52
NEX-4581 | bobg@backroads.com | Shiva | Done | TShirt Jersey Inventory (Weekly)** | 2019-06-05 09:57 | 5/23/2019 7:59
NEX-4616 | jesse_karp@backroads.com | Sai Sadanala | Done | TD: On Request Message** | 5/16/2019 17:07 | 5/22/2019 8:08
NEX-4384 | vinodp@BACKROADS.com | Satya | Done | Last Minute Changes to FTU | 1/25/2019 11:11 | 5/21/2019 15:40
NEX-4588 | jillt@backroads.com | Khaleel | Done | Update to Best Credits Applied issues Report | 2019-07-05 14:24 | 5/21/2019 9:50
NEX-4606 | jesse_karp@backroads.com | Balaji | Done | BOS Services Report** | 5/14/2019 8:23 | 5/21/2019 9:25
NEX-4544 | bobg@backroads.com | Venkatadri | Done | Cancellations of Carbon Bikes | 4/23/2019 8:00 | 5/20/2019 15:06
NEX-4553 | bobg@backroads.com | Khaleel | Done | Logistics/Equipment needs from FTR - Last 7 Days (weekly) | 4/24/2019 7:44 | 5/20/2019 14:39
NEX-4556 | bobg@backroads.com | Balaji | Done | Logistics/Equipment needs from FTR - North America (Daily) | 4/25/2019 8:16 | 5/20/2019 14:38
NEX-4576 | bobg@backroads.com | Venkatadri | Done | Area Survey Report (weekly) | 2019-02-05 14:41 | 5/16/2019 17:19
NEX-4603 | jesse_karp@backroads.com | Balaji | Done | Room Requests Outstanding** | 5/13/2019 10:13 | 5/16/2019 10:38
NEX-4543 | tommaso_spinelli@BACKROADS.com | Satya | Done | Create Subscription for Guest Address List for Guests report | 4/23/2019 7:42 | 5/16/2019 10:31
NEX-4519 | daniel_wootton@BACKROADS.com | Venkatadri | Done | Low Score Trip Alert | 3/31/2019 11:21 | 5/15/2019 8:50
NEX-4534 | ruths@BACKROADS.com | KhAleel | Done | SUBSCRIPTION UPDATES | 2019-11-04 15:24 | 2019-10-05 16:12
NEX-4540 | jillt@backroads.com | Sai Sadanala | Done | Best Club Reporting Enhancements/ Issues Review | 4/19/2019 8:13 | 2019-10-05 16:11
NEX-4557 | vinodp@BACKROADS.com | Satya | Done | Create Subscription for Guest with Small Trip Surcharge | 4/25/2019 9:35 | 2019-10-05 15:26
NEX-4508 | vinodp@BACKROADS.com | KhAleel | Done | Set up TC Eval Report to Auto-email | 3/27/2019 15:38 | 2019-10-05 15:26
NEX-3674 | amandal@backroads.com | Satya | Done | Guest Interest Survey Report | 7/24/2018 18:24 | 2019-10-05 15:26
NEX-4385 | sean_faley@backroads.com | Balaji | Done | Low Score Alert | 1/25/2019 12:44 | 2019-09-05 09:55
NEX-3788 | kch@backroads.com | Venkatadri | Done | Backroads Travel Agencies Booking in Trip Departure Date Range <mm/dd/yy> - <mm/dd/yy> | 7/27/2018 12:34 | 2019-08-05 16:51
NEX-3812 | amandal@backroads.com | Sai Sadanala | Done | Guest Passport list (airline) | 7/28/2018 12:03 | 2019-08-05 10:03
NEX-4466 | jillt@backroads.com | Khaleel | Done | Best Club Post Trip Credit | 2019-08-03 12:01 | 2019-02-05 08:51
NEX-3663 | louieo@backroads.com | Venkatadri | Done | Private Trip Performance Report | 7/24/2018 17:12 | 2019-02-05 08:00
NEX-4412 | michael_bernhard@backroads.com | Balaji | Done | Upcoming Ship Trip Notification (7 days out email) | 2019-01-02 15:27 | 2019-02-05 08:00
NEX-3843 | tommaso_spinelli@BACKROADS.com | Sai Sadanala | Done | Field Staff Performance Report | 7/30/2018 10:30 | 2019-02-05 08:00
NEX-4532 | ruths@BACKROADS.com | Shiva | Done | UPDATE FOR CMS DATA CHANGE Bookings/Holds-Waitlists/Cancellations for "SPECIAL" Trips Report | 2019-11-04 10:38 | 2019-02-05 07:51
NEX-3736 | amandal@backroads.com | Sai Sadanala | Done | Trip Departures: <mm/dd/yyyy> - <mm/dd/yyyy> (On-demand GSC-TIS report) | 7/25/2018 20:11 | 2019-02-05 07:51
NEX-4451 | amandal@backroads.com | Venkatadri | Done | TIS Departures within 8 Days (Former Guest Services Checklist, 2 Work Weeks Beginning Monday Report) | 2019-01-03 11:20 | 2019-02-05 07:51
NEX-3848 | sean_faley@backroads.com | Balaji | Done | Confidential Concerns Report | 7/30/2018 11:22 | 2019-02-05 07:51
NEX-3818 | jillt@backroads.com | Balaji | Done | BEST Milestone Fulfillment | 7/28/2018 12:12 | 2019-02-05 07:51
NEX-3646 | amandal@backroads.com | Sai Sadanala | Done | Trip-Beginning or Trip-End Flight: Guests Opting Out Report | 7/24/2018 14:17 | 2019-02-05 07:51
NEX-3670 | sean_faley@backroads.com | Khaleel | Done | Leader Addenda | 7/24/2018 17:16 | 2019-02-05 07:51
NEX-4358 | richs@backroads.com | Balaji | Done | Solo Tracking Report | 2019-10-01 09:45 | 2019-02-05 07:50